## Sheet1
Category	Task	Details	Time Estimation	Actual time
Backend (Copy)	Project rest API (C/R/U/D)		10m
	Project proto file		10m
	Project microservice		45m
	Project ORM		10m
	Postman calls		20m
		TOTAL	~ 1.5h	1h 15m
	Project view based on student view	(mostly copy paste with replace all)	10m	15m
Backend (Task)	management API (list, add, remove student)		10m
	Management proto		10m
	Management microservice		2h
	Management ORM		10m
	Postman calls		5m
		TOTAL	~ 2.5h	2h 15m